## Sheet1
milestone
Component | Milestone | Date | Team work days |  | Petal v0.0 | Petal v0.0 testing | Petal v0.1 | Enclosure v0.1 | Petal v0.1 testing | Petal v0.2 | Petal Datasheet | Enclosure v0.2 | Petal User Manual | AVAlink v1.0 beta | AVAlink v1.0 beta testing | AVAlink v1.0 | AVAlink Documentation
| v0.0 | 2024-10-01 | 1.6667 | Petal v0.0 | 10
| v0.0 testing | 2024-10-15 | 3.3333 | Petal v0.0 testing | x | 3.33
| v0.1 | 2024-10-29 | 1.6667 | Petal v0.1 | x |  | 3
| Enclosure v0.1 | 2024-11-01 | 1.6667 | Enclosure v0.1 |  |  | x | 2
| v0.1 testing | 2024-11-10 | 10 | Petal v0.1 testing |  |  | x |  | 3.33
| v0.2 | 2024-11-19 | 3.3333 | Petal v0.2 |  |  | x |  | x | 3
Petal | Datasheet | 2024-12-13 | 5 | Petal Datasheet | [5 empty] | x | 1.67
| Enclosure v0.2 | 2024-12-13 | 3.3333 | Enclosure v0.2 | [5 empty] | x |  | 1.67
| User Manual | 2024-12-13 | 5 | Petal User Manual | [5 empty] | x | x |  | 1.67
AVAlink | v1.0 beta | 2024-10-28 | 10 | AVAlink v1.0 beta | x | [8 empty] | 10
| v1.0 beta testing | 2024-11-11 | 1.6667 | AVAlink v1.0 beta testing | x | [9 empty] | 1.67
| v1.0 | 2024-12-13 | 6.6667 | AVAlink v1.0 |  |  | x | [8 empty] | 6.67
| Documentation | 2024-12-13 | 1.6667 | AVAlink Documentation | [11 empty] | x | 1.67
| Scope Document | 2024-09-09
| Proposal | 2024-09-20
| Gantt Chart | 2024-09-23
Project Documentation | Budget | 2024-09-30
| Proposal Presentation | 2024-10-03
| Risk Assessment | 2024-10-07
| Test Planning | 2024-10-21 |  | HARDWARE
| Progress Report | 2024-10-25
| Progress Presentation | 2024-10-31 |  | v0.0 | 2024-10-01 | 10
| Standards Document | 2024-11-04 |  |  | Schematic | PCB routing | review | test planning
| Ethics Document | 2024-11-18 |  | Schematic | 3 |  |  |  |  | name | date | time
| Web Page | 2024-11-22 |  | PCB routing | x | 4 | x |  |  |  | Test outline | Perform tests | Document data | Formal Write up
| Risk Audit | 2024-11-25 |  | review |  | x | 1 |  |  | Test outline
| Completion Audit | 2024-12-02 |  | test planning |  | x |  | 2 |  | Perform tests
| Formal Report | 2024-12-06 | [7 empty] | Document data
| Display | 2024-12-13 | [7 empty] | Formal Write up
| Final Presentation | 2024-12-13 |  | v0.0 testing | 2024-10-15 | 3.3
[5 empty] | Test outline | Perform tests | Document data | Formal Write up
|  |  |  | Test outline | 1
|  |  |  | Perform tests | x | 1
|  |  |  | Document data |  | x | 0.67
|  |  |  | Formal Write up |  | x | x | 0.67
|  |  |  | v0.1 | 2024-10-29 | 5
[5 empty] | review v0.0 test data | update schematic | update pcb | review pcb
|  |  |  | review v0.0 test data | 1
|  |  |  | update schematic | x | 1
|  |  |  | update pcb |  | x | 2 | x
|  |  |  | review pcb |  |  | x | 1