## Budget
Task Name | Milestone | Duration (days) | Duration Hours (8hr/day x3 ppl) | Start | Finish | Resource Names | Labour cost ($10/hr) | Parts cost | Total Cost | Milestone Expected Cost
1. Petal v0.0 Schematic |  | 5 | 120 | Sat 24-09-21 | Wed 24-09-25 | Labour | 1200 | 0 | 1200
2. PCB v0.0 |  | 3 | 72 | Wed 24-09-25 | Fri 24-09-27 | Labour | 720 | 0 | 720
3. PCB v0.0.1 (revision) |  | 4 | 96 | Sat 24-09-28 | Tue 24-10-01 | Labour, Parts | 960 | 0 | 960
4. Petal v0.0 | 1st PCB submission | 0 | 0 | Tue 24-10-01 | Tue 24-10-01 | n/a | 0 | 0 | 0 | 2880
5. AVAlink v1.0 beta Development |  | 30 | 720 | Tue 24-09-03 | Wed 24-10-02 | Labour | 7200 | 0 | 7200
6. Petal v0.0 Testing |  | 4 | 96 | Wed 24-10-02 | Sat 24-10-05 | Labour | 960 | 78.18 | 1038.18
7. AVAlink v1.0 beta testing |  | 5 | 120 | Thu 24-10-03 | Mon 24-10-07 | Labour | 1200 | 0 | 1200
8. Petal v0.1 | 2nd PCB submission | 4 | 96 | Sun 24-10-06 | Wed 24-10-09 | Labour, Parts | 960 | 78.18 | 1038.18 | 13356.36
9. Enclosure v0.1 |  | 6 | 144 | Thu 24-10-10 | Tue 24-10-15 | Labour,Parts | 1440 | 52.58 | 1492.58
10. AVAlink v1.0 Development |  | 10 | 240 | Tue 24-10-08 | Thu 24-10-17 | Labour | 2400 | 0 | 2400
11. Petal v0.1 testing |  | 4 | 96 | Fri 24-11-8 | Mon 24-11-11 | Labour | 960 | 0 | 960
12.Enclosure v0.2 |  | 5 | 120 | Fri 24-11-15 | Tue 24-11-19 | Labour,Parts | 1200 | 52.58 | 1252.58
13. AVAlink Documentation |  | 5 | 120 | Mon 24-12-09 | Fri 24-12-13 | Labour | 1200 | 0 | 1200
14. AVAlink v1.0 | End date: Software Prototype | 0 | 0 | Fri 24-12-13 | Fri 24-12-13 | n/a | 0 | 0 | 0 | 20661.52
1. Petal v0.2 | End date: Hardware Prototype | 0 | 0 | Fri 24-12-13 | Fri 24-12-13 | n/a | 0 | 0 | 0 | 20661.52
[6 empty] | TOTAL LABOUR | 20400
[6 empty] | TOTAL PARTS (2 prototype boards & enclosures) |  | 261.52

## RevExp
Revenue
Camosun Capstone Funding | 250
Student Donation (Parts) | 300
Student Donation (Labour) | 20111.52
20661.52
Expenses
Labour | 20400
Parts | 261.52
20661.52
TOTAL (Revenue-Expenses) | 0

## Audit
BUDGET TO DATE
Task Name | Expected Duration (days) | Duration Hours (8hr/day x3 ppl) | Expected Start | Expected Finish | Resource Names | Expected Labour cost ($10/hr) | Expected Parts Cost | Total Expected Cost
1. Petal v0.0 Schematic | 5 | 120 | Sat 24-09-21 | Wed 24-09-25 | Labour | 1200 | 0 | 1200
2. PCB v0.0 | 3 | 72 | Wed 24-09-25 | Fri 24-09-27 | Labour | 720 | 0 | 720
3. PCB v0.0.1 (revision) | 4 | 96 | Sat 24-09-28 | Tue 24-10-01 | Labour | 960 | 0 | 960
AUDIT (MILESTONE 1: OCT 2, 2024)
Task Name | Actual Duration (days) | Duration Hours (8hr/day x3 ppl) | Actual Start | Actual Finish | Resource Names | Actual Labour Cost ($10/hr) | Actual Parts Cost | Total Actual Cost | Task Expected Cost - Actual Cost | Task Budget Description
1. Petal v0.0 Schematic | 7 | 168 | Sat 24-09-21 | Fri 24-09-27 | Labour | 1680 | 0 | 1680 | -480 | Overbudget
2. PCB v0.0 | 2 | 48 | Fri 24-09-27 | Sat 24-09-28 | Labour | 480 | 0 | 480 | 240 | Underbudget
3. PCB v0.0.1 (revision) | 4 | 96 | Sun 24-09-29 | Wed 24-10-02 | Labour | 960 | 0 | 960 | 0 | On Budget
[8 empty] | Cumulative Expected Cost |  | 2880
[8 empty] | Cumulative Actual Cost |  | 3120
notes: To date all expenses have been from personnel labour costs. | [7 empty] | TOTAL |  | -240 | overbudget to date, 1 day behind schedule

## BOM
Enclosure (Task 9, 11)
VENDOR: Amazon.ca
No. | Qty | Manufacturer Part # | Vendor Part # | Link to Part (URL) | Shipping From ( Country ) | Detailed Part Description | PCB Footprint | Unit Price ($CDN) | Extended Price
1 | 1 | n/a | n/a | https://www.amazon.ca/LMioEtool-Dustproof-Waterproof-Electrical-220mmx170mmx110mm/dp/B07KXSJ4J2/ref=sr_1_4?crid=1WZAW818TQA1Z&dib=eyJ2IjoiMSJ9.wHTWRIqfUsUzQewbBFOE4dOcs5e9pPfsqIt6GL1JW8pf_G36KQkoDtZhRXPgHND2cKA3WxYCmA-nW21SixuDMtO4HBGSlu1jfJLfdXX9GMuvCOonqw0KFt-89O1MXVY0.z6fapAWZWkRHFqOxaeAqwkKibT2iBVJYYkNV3b4_Y04&dib_tag=se&keywords=4%22x4%22+pvc+inclosure&qid=1727740572&sprefix=4+x4+pvc+inclosure%2Caps%2C141&sr=8-4 | Canada | IP65 Junction Box (8.7"x6.7"x4.3") | n/a | 36.99 | 36.99
2 | 1 | n/a | n/a | https://www.amazon.ca/LeMotech-Waterproof-Adjustable-Connectors-Gaskets/dp/B08ZY5186W/ref=sr_1_3_sspa?crid=3QQ5BE80XIC6B&dib=eyJ2IjoiMSJ9.wm_OBrTT0WCGT3n5w40Dzgsb4Sek3ejoiQseRrQGMnpCJC4hKERwlj8LElrArCG1pjPEPJVsNnRZUSbwDdFUHCrhFko6Ur-JCeHL1JTSXv8FjSngf_jAsTXxrSYzBQQ837zOP4pwOVkxPxqjV5VPVPJb9gL7S82R_mPUOK3uaaCxYr1KPCMZWan98wrhE74Jiq3H1g38gf8eL3yS_ppUezD4_lN2BtQ9Ya9g-1c9FpiWLzN3RLQED4h4LGQxR7Sqq5ZsQqf0701pRAjLi3CdLACx0Y_pywO4TG_xUYG-JK4.BjR2ruoq4s9pYa9yaymhJSKe3OLMOvLaH_Ppyh5PkMU&dib_tag=se&keywords=waterproof%2Bcable%2Bgland&qid=1727741163&sprefix=waterproof%2Bcable%2Caps%2C198&sr=8-3-spons&sp_csd=d2lkZ2V0TmFtZT1zcF9hdGY&th=1 | Canada | NPT 1/2" Cable Glands Waterproof x5 | n/a | 15.59 | 15.59
|  |  | 15.59 | 31.18
[7 empty] | Cost/Enclosure |  | 52.58
PCB components: Prototyping Board (Petal v0.0 Task 6)
VENDOR: MOUSER
No. | Qty | Manufacturer Part # | Vendor Part # | Link to Part (URL) | Shipping From ( Country ) | Detailed Part Description | PCB Footprint | Unit Price ($CDN) | Extended Price
1 | 7 | GCM21BR72A104KA37L | 81-GCM21BR72A104KA7L | https://www.mouser.ca/ProductDetail/Murata-Electronics/GCM21BR72A104KA37L?qs=aEuGZpxfbxU57i7kalIPTw%3D%3D | Canada | 100 nF Ceramic Capacitor - C1, C5, C6, C7, C8, C9, C12 | 0805 | 0.091 | 0.637
2 | 2 | GRM21BR60J226ME39L | 81-GRM21R60J226ME39L | https://www.mouser.ca/ProductDetail/Murata-Electronics/GRM21BR60J226ME39L?qs=DJY02EClX9n4vY1%2FNV53Qw%3D%3D | Canada | 22uF Ceramic Capacitor - C2, C11 | 0805 | 0.435 | 0.87
3 | 1 | GCJ219R71C105KA01D | 81-GCJ219R71C105KA1D | https://www.mouser.ca/ProductDetail/Murata-Electronics/GCJ219R71C105KA01D?qs=TpyF2b7C1Q%252BYYZPnEdny3Q%3D%3D | Canada | 1uF Ceramic Capacitor - C3 | 0805 | 0.305 | 0.305
4 | 2 | GRM21BR61E106KA73L | 81-GRM21BR61E106KA3L | https://www.mouser.ca/ProductDetail/Murata-Electronics/GRM21BR61E106KA73L?qs=Uw8ySfEHS7LOsCQEzvRcNg%3D%3D | Canada | 10uF Ceramic Capacitor - C10, C4 | 0805 | 0.363 | 0.726
5 | 2 | GRM21BR61E106KA73L | 810-C3216X5R1E476M | https://www.mouser.ca/ProductDetail/TDK/C3216X5R1E476M160AC?qs=NRhsANhppD%252BqapdVvBvu4Q%3D%3D | Canada | 47 uF Capacitor - C13,C14 | 1206 | 1.48 | 2.96
6 | 1 | GRT31CR61H106KE01L | 81-GRT31CR61H106KE1L | https://www.mouser.ca/ProductDetail/Murata-Electronics/GRT31CR61H106KE01L?qs=drgMNd%252BkGPOfk81gMUj0ow%3D%3D | Canada | 10 uF Capacitor - C15 | 1206 | 0.899 | 0.899
7 | 1 | C0603C104Z4VACTU | 80-C0603C104Z4V | https://www.mouser.ca/ProductDetail/KEMET/C0603C104Z4VACTU?qs=t9q%2F2xDdjt80hHjNGtEgzg%3D%3D | Canada | 100 nF Ceramic Capacitor - C16 | 0603 | 0.145 | 0.145
8 | 3 | GRM32ER61E226KE15L | 81-GRM32ER61E226KE15 | https://www.mouser.ca/ProductDetail/Murata-Electronics/GRM32ER61E226KE15L?qs=CHiu0TXTCq%252Bo%252Bcqcz70txw%3D%3D | Canada | 22uF Ceramic Capacitor - C17,C20,C21 | 1210 | 2.55 | 7.65
9 | 1 | GRM21BR61E106MA73L | 81-GRM21BR61E106MA3L | https://www.mouser.ca/ProductDetail/Murata-Electronics/GRM21BR61E106MA73L?qs=2W5sgKM%2F371odLMyCilkag%3D%3D | Canada | 10 uF Capacitor - C18 | 0805 | 0.319 | 0.319
10 | 1 | 06033C104KAT2A | 581-06033C104KAT2A | https://www.mouser.ca/ProductDetail/KYOCERA-AVX/06033C104KAT2A?qs=gPDEucxdFwYuZhv3uXRdIw%3D%3D | Canada | 100 nF Ceramic Capacitor - C19 | 0603 | 0.145 | 0.145
11 | 1 | GRM32EC80J107ME20L | 81-GRM32EC80J107ME0L | https://www.mouser.ca/ProductDetail/Murata-Electronics/GRM32EC80J107ME20L?qs=eCxWOFGThBZyUCwIudAIww%3D%3D | Canada | 100uF Ceramic Capacitor - C20 | 1210 | 2.55 | 2.55
12 | 1 | TPSB475K035R0700 | 581-TPSB475K035R0700 | https://www.mouser.ca/ProductDetail/KYOCERA-AVX/TPSB475K035R0700?qs=vV7MX5mTKGOnhbxp1nxMNw%3D%3D | Canada | 4.7uF Tantalum Capacitor - C23 | 1210 | 1.07 | 1.07
13 | 1 | ECH-U1H821JX5 | 667-ECH-U1H821JX5 | https://www.mouser.ca/ProductDetail/Panasonic/ECH-U1H821JX5?qs=nKUIxd1C0NJegDRFXgQx8Q%3D%3D | Canada | 820 pF Film Capacitor - C24 | 0805 | 0.522 | 0.522
14 | 2 | 1N5819HW-7-F | 621-1N5819HW-F | https://www.mouser.ca/ProductDetail/Diodes-Incorporated/1N5819HW-7-F?qs=NQ47qNm99eDyWTEd07miYA%3D%3D | Canada | SMT Schottky diode - D1.D3 | SOD-123-2 | 0.595 | 1.19
15 | 1 | 150505M173300 | 710-150505M173300 | https://www.mouser.ca/ProductDetail/Wurth-Elektronik/150505M173300?qs=fAHHVMwC%252Bbi%2FURn4Qu0%2FAA%3D%3D | Canada | SMT RGB LED - D2 | Custom SMT | 0.914 | 0.914
16 | 3 | ESD5B5.0ST1G | 863-ESD5B50ST1G | https://www.mouser.ca/ProductDetail/onsemi/ESD5B5.0ST1G?qs=bTNLGnZZEJg%2Fr8bn3zOMJw%3D%3D | Canada | SMT Protection Diode - D4, D5, D6 | SOD-523-2 | 0.319 | 0.957
17 | 2 | 61300611821 | 710-61300611821 | https://www.mouser.ca/ProductDetail/Wurth-Elektronik/61300611821?qs=iLbezkQI%252BsgS21jF2eozhA%3D%3D | Canada | 6 position female header - J1,J2 | THT | 0.522 | 1.044
18 | 2 | 1729128 | 651-1729128 | https://www.mouser.ca/ProductDetail/Phoenix-Contact/1729128?qs=GFUSqQMLmmnCBVBY3dts9w%3D%3D | Canada | 2 position screw terminal - J3,J10 | THT | 1.13 | 2.26
19 | 1 | 10103594-0001LF | 649-10103594-0001LF | https://www.mouser.ca/ProductDetail/Amphenol-FCI/10103594-0001LF?qs=EnLMdcWnKABYZwdMsmC%2Fag%3D%3D | Canada | SMT Micro USB Port - J4 | Custom SMT | 1.2 | 1.2
20 | 1 | MEM2061-01-188-00-A | 640-MEM20610118800A | https://www.mouser.ca/ProductDetail/GCT/MEM2061-01-188-00-A?qs=KUoIvG%2F9IlYc25USp0M1eQ%3D%3D | Canada | SMT SD Card reader - J5 | Custom SMT | 1.74 | 1.74
21 | 1 | 74479299222 | 710-74479299222 | https://www.mouser.ca/ProductDetail/Wurth-Elektronik/74479299222?qs=16w8nSHsg3tcdL6pYOiu3w%3D%3D | Canada | SMT Power Inductor - L1 | 1210 | 1.39 | 1.39
22 | 1 | IHLP3232DZER4R7M1 | 70-IHLP3232DZER4R7M1 | https://www.mouser.ca/ProductDetail/Vishay-Dale/IHLP3232DZER4R7M11?qs=Nbmv7C3%2FzlBkjG9ees3Knw%3D%3D | Canada | SMT Power Inductor - L2 | 3232 | 1.83 | 1.83
23 | 1 | TPSM84203EAB | 595-TPSM84203EAB | https://www.mouser.ca/ProductDetail/Texas-Instruments/TPSM84203EAB?qs=EU6FO9ffTwdvD6IyQBtt5A%3D%3D | Canada | DC-DC switching Regulator - MD1 | THT | 10.69 | 10.69
24 | 2 | MMBT3904-F | 621-MMBT3904-F | https://www.mouser.ca/ProductDetail/Diodes-Incorporated/MMBT3904-7-F?qs=7F%2FY8wl6X3H3eL7tHVWSBQ%3D%3D | Canada | SMT NPN BJT Transistors - Q1, Q2 | SOT-23-3 | 0.145 | 0.29
25 | 1 | ERJ-6GEY0R00V | 667-ERJ-6GEY0R00V | https://www.mouser.ca/ProductDetail/Panasonic/ERJ-6GEY0R00V?qs=tQNqqtTOejLLHbaWAzeH1w%3D%3D | Canada | SMT 0R Resistor - R1 | 0805 | 0.145 | 0.145
26 | 4 | ERJ-6ENF1002V | 667-ERJ-6ENF1002V | https://www.mouser.ca/ProductDetail/Panasonic/ERJ-6ENF1002V?qs=4WZYzuGhm5pfKPfuMiCO5g%3D%3D | Canada | SMT 10K Resistor - R2, R4, R8, R29 | 0805 | 0.16 | 0.64
27 | 1 | ERJ-8GEY0R00V | 667-ERJ-8GEY0R00V | https://www.mouser.ca/ProductDetail/Panasonic/ERJ-8GEY0R00V?qs=js9DCdkuA2qAJlMAuBQJEA%3D%3D | Canada | SMT 0R Resistor 1/2 W- R3 | 1206 | 0.189 | 0.189
28 | 3 | RNCP0805FTD100R | 708-RNCP0805FTD100R | https://www.mouser.ca/ProductDetail/SEI-Stackpole/RNCP0805FTD100R?qs=FESYatJ8odKa%252Bzqp4gsQrw%3D%3D | Canada | SMT 100R Resistor - R5, R7, R10 | 0805 | 0.145 | 0.435
29 | 1 | ERJ-6ENF4990V | 667-ERJ-6ENF4990V | https://www.mouser.ca/ProductDetail/Panasonic/ERJ-6ENF4990V?qs=tQNqqtTOejJ8SQeWozY0bw%3D%3D | Canada | SMT 499R - R6 | 0805 | 0.16 | 0.16
30 | 1 | ERJ-6GEY0R00V | 667-ERJ-6GEY0R00V | https://www.mouser.ca/ProductDetail/Panasonic/ERJ-6GEY0R00V?qs=tQNqqtTOejLLHbaWAzeH1w%3D%3D&srsltid=AfmBOorkzjg5B0Qf1TJYeMrZE5TXBvtH40kFjShMvjev2YVWUa8F6NLZ | Canada | SMT Resistor Zero Ohms - R9 | 0805 | 0.145 | 0.145
31 | 1 | ERJ-6ENF1501V | 667-ERJ-6ENF1501V | https://www.mouser.ca/ProductDetail/Panasonic/ERJ-6ENF1501V?qs=4WZYzuGhm5qa4PPEzdMS5A%3D%3D | Canada | SMT Resistor 1.5Kohms- R11 | 0805 | 0.16 | 0.16
32 | 2 | RMCF0805FT100R | 708-RMCF0805FT100R | https://www.mouser.ca/ProductDetail/SEI-Stackpole/RMCF0805FT100R?qs=FESYatJ8odIZDyKRWKfVQQ%3D%3D&srsltid=AfmBOoqRMHEDlgWWRUUh1x52dT8c7v6QL7bVnax5KZtwueVMTq7J9ihL | Canada | SMT Resistor 100Ohms -R12, R13 | 0805 | 0.145 | 0.0725
33 | 1 | CRCW0603100KFKEA | 71-CRCW0603-100K-E3 | https://www.mouser.ca/ProductDetail/Vishay-Dale/CRCW0603100KFKEA?qs=6dqgS%252BKntICWHMMdIzt5%2FQ%3D%3D&srsltid=AfmBOooGLNUTNo5F3cI_PorlFSAxPbW9BP25Zjkx0z05bmh2-uMjp_uy | Canada | SMD resistor 100Kohms 1/10watt - R14 | 0603 | 0.145 | 0.145
34 | 1 | RC0603FR-0730K9L | 603-RC0603FR-0730K9L | https://www.mouser.ca/ProductDetail/YAGEO/RC0603FR-0730K9L?qs=diQw95jMAeMZrPIXfOkmFA%3D%3D&srsltid=AfmBOopD6znLDF1B8MY9TQ_wBrc-DL_-O7DIcraqYxXRL91-qZReFuyP&_gl=1*gb5wwx*_ga*MTMwNTkzNzQzNy4xNzI2Njc0NDU2*_ga_15W4STQT4T*MTcyNzc1Njk5Ny4zLjAuMTcyNzc1Njk5OS41OC4wLjA.*_ga_1KQLCYKRX3*dW5kZWZpbmVk | Canada | SMD resistor 30.9 kOhms - R15 | 0603 | 0.145 | 0.145
35 | 1 | CRCW060310K0FKEA | 71-CRCW0603-10K-E3 | https://www.mouser.ca/ProductDetail/Vishay-Dale/CRCW060310K0FKEA?qs=pAO1Z172M84BVnhDjtnsoQ%3D%3D | Canada | Thick Film Resistor - SMD 1/10watt 10Kohms 1% -R17 | 0603 | 0.145 | 0.145
36 | 3 | ERJ-6ENF2703V | 667-ERJ-6ENF2703V | https://www.mouser.ca/ProductDetail/Panasonic/ERJ-6ENF2703V?qs=50QC8w71jAsIUsFp0TwUKw%3D%3D&srsltid=AfmBOooMU2HzTazfHQQ_GilVJBOmrPOzdSr-KLuhTXvPHQ_8uEBMs9Sr | Canada | Thick Film Resistors - SMD 270Kohms - R18, R19, R23 | 0805 | 0.145 | 0.435
37 | 4 | ERJ-6ENF1073V | 667-ERJ-6ENF1073V | https://www.mouser.ca/ProductDetail/Panasonic/ERJ-6ENF1073V?qs=JjxTDIFmKPR8KLEztkGZyw%3D%3D&srsltid=AfmBOoo_cLf-iInytaw5RELcitcTwyfDzLFqUS61yKkIRJ2grf6534v5 | Canada | Thick Film Resistors - SMD 0805 107Kohms - R20, R21, R27, R28 | 0805 | 0.145 | 0.58
38 | 1 | ERJ-6ENF4023V | 667-ERJ-6ENF4023V | https://www.mouser.ca/ProductDetail/Panasonic/ERJ-6ENF4023V?qs=50QC8w71jAs%252BYzJfgzNd5w%3D%3D&srsltid=AfmBOopAOuD687YPxl75fDzQEsjcQ6yxrwZvuqC5Fsxm6MQQoAUPytm6 | Canada | Thick Film Resistors - SMD 0805 402Kohms - R22 | 0805 | 0.145 | 0.145
39 | 1 | ERJ-6ENF5902V | 667-ERJ-6ENF5902V | https://www.mouser.ca/ProductDetail/Panasonic/ERJ-6ENF5902V?qs=50QC8w71jAsddX83LVzkRA%3D%3D&srsltid=AfmBOoqe-bjRGmovNW-sHFVTv72RT0nvuAl_EvZI0KQ1eb_oHwDRR40M | Canada | Thick Film Resistors - SMD 59Kohms - R24 | 0805 | 0.16 | 0.16
40 | 1 | ERJ-6ENF1182V | 667-ERJ-6ENF1182V | https://www.mouser.ca/ProductDetail/Panasonic/ERJ-6ENF1182V?qs=JjxTDIFmKPQZscRXwQ1smA%3D%3D&srsltid=AfmBOopyxwAPUK3t6A5N2nQSwJ16XL0NCh-Z8RG9x1Uy4Hpi_4o6J56F | Canada | Thick Film Resistors - SMD 0805 11.8Kohms - R25 | 0805 | 0.145 | 0.145
41 | 1 | ERJ-6ENF4022V | 667-ERJ-6ENF4022V | https://www.mouser.ca/ProductDetail/Panasonic/ERJ-6ENF4022V?qs=tQNqqtTOejK24%252BpEKJjobQ%3D%3D&srsltid=AfmBOorYyD9BxsCXzmOGMgyQaRGib3EYtzCPM2qYcWsW_D0hLkm3zEW7 | Canada | Thick Film Resistors - SMD 0805 40.2Kohms -R26 | 0805 | 0.16 | 0.16
42 | 3 | PTS526 SK15 SMTR2 LFS | 611-PTS526SK15SMR2L | https://www.mouser.ca/ProductDetail/CK/PTS526-SK15-SMTR2-LFS?qs=UXgszm6BlbF5Ezp94JAQtw%3D%3D&srsltid=AfmBOoraraNhY22iVWPvuqZSt6ZX4rBrJ9YlAnyR2G0X3AOLYMwh4ZpP | Canada | Tactile Switches 50mA 12VDC - SW1, SW2, SW3 | SMT | 0.203 | 0.609
43 | 3 | 5019 | 534-5019 | https://www.mouser.ca/ProductDetail/Keystone-Electronics/5019?qs=wOxb8XianXjjCAsb90Ilzw%3D%3D&srsltid=AfmBOoqVE_KfdvxRLYcEhlSmWn4Kk8fFnxp4bmaR1vJVr7Qvx7YQxJJt | Canada | Test Point - TP1, TP2, TP3 | SMT | 0.341 | 1.023
44 | 1 | ESP32-S3-MINI-1-N8 | 356-ESP32-S3-MINI1N8 | https://www.mouser.ca/ProductDetail/Espressif-Systems/ESP32-S3-MINI-1-N8?qs=XAiT9M5g4x82rl6F%2FIYUQg%3D%3D | Canada | Multiprotocol Modules SMD module, ESP32-S3FN8, 8 MB SPI flash, PCB antenna -U1 | SMT | 4.5 | 4.5
45 | 1 | core1262-HF | 20855 | https://www.waveshare.com/core1262-868m.htm?sku=20855 | China | core1262-HF Lora Module based around the semtech 1262 chip. This module can be purchased for two frequency bands. Please ensure the core 1262-HF variant is selected. U2 | SMT | 10.85 | 10.85
46 | 1 | TPS62933PDRLR | 595-TPS62933PDRLR | https://www.mouser.ca/ProductDetail/Texas-Instruments/TPS62933PDRLR?qs=vvQtp7zwQdPCuPvhGs%2FYxA%3D%3D | Canada | Switching Voltage Regulators 3.8-V to 30-V, 3-A, 200-kHz to 2.2-MHz, low-IQ synchronous buck converter in SOT-583 8-SOT-5X3 -40 to 150 | SOT-583-8 | 1.65 | 1.65
47 | 1 | TPSM84203EAB | 595-TPSM84203EAB | https://www.mouser.ca/ProductDetail/Texas-Instruments/TPSM84203EAB?qs=EU6FO9ffTwdvD6IyQBtt5A%3D%3D&_gl=1*2nm9zf*_ga*MjA1MjYwNTc4MS4xNzI3MTM3ODQ0*_ga_15W4STQT4T*MTcyNzEzNzg0NC4xLjAuMTcyNzEzNzg0Ny41Ny4wLjA. | CAN | Non-Isolated DC/DC Converters 1.5A, 28V Input, 3.3V Output, TO-220 Power Module 3-SIP MODULE -40 to 125 | Through Hole | 9.61 | 9.61
48
49
50
[7 empty] | Mouser Total |  | 74.5515
VENDOR: Digikey
51 | 2 | PREC003SAAN-RC | PREC003SAAN-RC | https://www.digikey.ca/en/products/detail/sullins-connector-solutions/PREC003SAAN-RC/2774851?s=N4IgTCBcDaIAoCUCiBhADGgzAZQIK4DkBaBFEAXQF8g | Canada | 3-Pin Male Header - J6,J8 | THT | 0.6 | 1.2
52 | 1 | PPPC122LFBN-RC | S7115-ND | https://www.digikey.ca/en/products/detail/sullins-connector-solutions/PPPC122LFBN-RC/810251?s=N4IgTCBcDaIAoIMIEYxgDIDEBCA5AtAEqIgC6AvkA | Canada | 24 Pin Female Header - P1 | THT | 2.69 | 0.81
53 | 2 | 61300621121 | 732-5295-ND | https://www.digikey.ca/en/products/detail/würth-elektronik/61300621121/4846835?s=N4IgTCBcDaIGwEYDMAGFcwIZkBdAvkA | Canada | 6 Pin 2 Row Male Header - P2, P3 | THT | 0.81 | 1.62
[7 empty] | DigiKey Total |  | 3.63
[7 empty] | Cost/board |  | 78.1815