## Sheet1
RISK ASSESSMENT FLoRa comms
No. | Description | Probability | Impact | Risk | Response | Outcome
1 | PCB will contain schematic/routing errors | MEDIUM | HIGH | MEDIUM-HIGH | Avoid - Proof-reading of board by all team members prior to ordering. Undergo design revisions advised by Capstone committee. | Minor time increase
2 | Initial PCB design will take longer than scheduled due to unanticipated revisions | MEDIUM | LOW | LOW | Accept - accept that this portion of development may take longer than anticipated and adjust scheduling accordingly. | Minor time increase
3 | PCB order will be lost by DHL shipping | LOW | LOW | LOW | Accept - as there will be a tracking number associated with our order, we will accept the risk of our shipment being lost as unlikely and in the event it is lost, the delay will not be long. | Minor time increase
4 | The switching power supply will interfere with radio and data TX/Rx signals. | MEDIUM | HIGH | MEDIUM-HIGH | Mitigate - Create a custom shielding cap for the power supply. | Small budget and short time increase.
5 | Development of prototype software will take longer than estimated. | HIGH | LOW | MEDIUM | Avoid -update milestones, scheduling and asignment of tasks regularly to adapt to changes in estimated development times. | Minor time increase associated with updates to the GitHub project management tool.
6 | Supplying batteries for our prototype is too costly | HIGH | HIGH | HIGH | Transfer - Notify the customer that they will have to provide batteries for the units. | Project remains on budget.